## Tabelle1
Embedded Systems Laboratory 2023 Timeline
Task | Responsible | Time
|  | March |  | April |  |  |  | May
|  | KW12 | KW13 | KW14 | KW15 | KW16 | KW17 | KW18 | KW19 | KW20 | KW21 | KW22
Group registration | Dino
Create project proposal | all
Project proposal V1 | all
Update project proposal | all
Final project proposal | all
Defining hardware | all
Ordering required hardware | Dino
Ordering required hardware (after recived feedback) | Dino
Setting up cloud basic functionality | Carlos and Shravya
Water level detection sensor (programming and cloud implementation) | Carlos
Moisture sensor and light resistor (programming and cloud implementation) | Dino
Waterpump and temperature sensor (programming and cloud implementation) | Shravya
Hardware finished | all
Mid term presentation | all
Implementation of waterpump and temperature sensor finished | Shravya
Implementation moisture sensor and light resistor finished | Dino
Implementation of water level detection sensor and cloud progamming finished | Carlos
Updating presentation after recived feedback | Carlos and Shravya
Video of the working project | all
Technical report | all
Project finished | all