## Tabelle1
Embedded Systems Laboratory 2023 Timeline
Task | Responsible | Time
|  | March |  | April |  |  |  | May
|  | KW12 | KW13 | KW14 | KW15 | KW16 | KW17 | KW18 | KW19 | KW20 | KW21 | KW22
Group registration | Dino
Create project proposal | all
Project proposal V1 | all
Update project proposal | all
Final project proposal | all
Defining hardware | Carlos
Ordering required hardware | Dino
Setting up moisture sensor | Carlos
Setting up waterpump | Shravya
Hardware finished | all
Mid term presentation | all
Cloud progamming | Carlos
Moisture Sensor programming | Dino
Waterpump programming | Shravya
Software waterpump finished | Shravya
Software sensor finished | Dino
Cloud progamming finished | Carlos
Video of the working project | all
Technical report | all
Time buffer | all
Project finished | all